## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Can't show map detail | Can't zoom the map to see detail | 1 | https://github.com/QuyQuoc2002/SWP-Team3/issues/6#issue-1571847923 | Closed | CongNT | 2023-01-11 | 2023-01-14 | iter1 | Task, 3_Done | HomepageManage
Can't connect ggmap | Can't connect ggmap | 2 | https://github.com/QuyQuoc2002/SWP-Team3/issues/8#issue-1571857243 | Closed | TaiNN | 2023-01-31 | 2023-02-03 | iter1 | Task, 3_Done | ApartmentManage
Fix ERD | Fix Account and UserInfo Entity, add City and District entity | 3 | https://github.com/QuyQuoc2002/SWP-Team3/issues/7#issue-1571855310 | Closed | VietNH | 2023-01-18 | 2023-01-20 | iter1 | Task, 3_Done | User Login
Add floor issue | Can add previously available floors | 4 | https://drive.google.com/file/d/1jpsgHTbLgKQrY4NjjKEY9WTUfvZOPPiF/view | Closed | ChienNK | 2023-02-08 | 2023-02-11 | iter2 |  | CRUD floor
Add floor issue | Issue when ordering existing floors | 5 | https://drive.google.com/file/d/1-yfs1x8QYZz7YkFuaS8kO0glvPzAvTpG/view | Closed | ChienNK | 2023-02-09 | 2023-02-11 | iter2 |  | CRUD floor
Add floor issue | Can add previously available floors when add space in floor name | 6 | https://drive.google.com/file/d/1G4SPUoSIA8tTHdDaFmxi8cLtyqMA7iM_/view | Closed | ChienNK | 2023-02-09 | 2023-02-11 | iter2 |  | CRUD floor
Add floor issue | When the apartment has no floors and press the save button, the screen is white | 7 | https://drive.google.com/file/d/1ZoQ1izSjqf7JxxzmVnw_Qvo0naynaQOo/view | Closed | ChienNK | 2023-02-10 | 2023-02-13 | iter2 |  | CRUD floor
Delete roomtype | When deleting a room type with rooms, that room type is deleted but page 404 . is displayed | 8 | https://drive.google.com/file/d/1ATAmpULZBxbSPoAqa4q6dlDP2h126NbH/view | Closed | TaiNN | 2023-02-18 | 2023-02-19 | iter2 |  | Delete roomtype
Can't add vehical | When adding vehical for tenant, add failed and page 404 is displayed | 9 | https://drive.google.com/file/d/1QQJrIEsh2ULE66mPJRYP_OTgD8O1k9rX/view | Closed | QuocPQ | 2023-02-18 | 2023-02-19 | iter2 |  | Add vehical